## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Madhukiran | 2026-04-09 | M2 Analytics navigation opening incorrect milestone view | Sprint 1 | Backend Team | Functional | Fixed sidebar routing logic | 2026-04-10 | Closed
2 | Madhukiran | 2026-04-09 | M3 purchase flow showing duplicate purchase requirement | Sprint 1 | Backend Team | Logic | Fixed payment and workflow state handling | 2026-04-10 | Closed
3 | Madhukiran | 2026-04-09 | M4 Career Trends chart appearing more than once | Sprint 1 | Backend Team | UI | Removed duplicate chart rendering | 2026-04-10 | Closed
4 | Madhukiran | 2026-04-09 | Runtime database files included in project staging | Sprint 2 | Backend Team | Configuration | Excluded runtime databases using .gitignore | 2026-04-10 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others