## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Madhukiran | 2026-09-11 | Research API timeout error | Sprint 1 | Madhukiran | Functional | Added retry logic | 2026-09-11 | Closed
2 | Madhukiran | 2026-09-11 | Planning Agent output not formatted | Sprint 1 | Madhukiran | UI | Fixed formatting in prompt | 2026-09-11 | Closed
3 | Madhukiran | 2026-09-11 | Frontend not connecting to backend | Sprint 2 | Madhukiran | Integration | Fixed CORS in FastAPI | 2026-09-11 | Closed
4 | Madhukiran | 2026-09-11 | Analysis Agent returning empty pros/cons | Sprint 2 | Madhukiran | Functional | Improved system prompt | 2026-09-11 | Closed
5 | Madhukiran | 2026-09-11 | Final decision page loading slowly | Sprint 2 | Madhukiran | Performance | Added loading spinner | 2026-09-11 | Closed
6 | Madhukiran | 2026-09-17 | Tool selection routing incorrect for some tools | Sprint 3 | Madhukiran | Functional | Updated ToolSelector routing logic | 2026-09-17 | Closed
7 | Madhukiran | 2026-09-17 | Data Validation request routed to wrong tool | Sprint 3 | Madhukiran | Functional | Corrected validation tool category and routing priority | 2026-09-17 | Closed
8 | Madhukiran | 2026-09-18 | Study Planner repeated the same activities across days | Sprint 3 | Madhukiran | Functional | Added distinct day-wise study stages and activities | 2026-09-18 | Closed
9 | Madhukiran | 2026-09-19 | Web Search displayed raw placeholder and demo text | Sprint 3 | Madhukiran | UI / Functional | Updated response generator to return human-readable summaries | 2026-09-19 | Closed
10 | Madhukiran | 2026-09-19 | M2 result displayed unnecessary Human-Readable Answer heading | Sprint 3 | Madhukiran | UI | Removed technical result heading from Streamlit interface | 2026-09-19 | Closed
11 | Madhukiran | 2026-09-20 | Streamlit request field showed accessibility warning | Sprint 3 | Madhukiran | UI | Added proper hidden label to text area | 2026-09-20 | Closed
12 | Madhukiran | 2026-09-20 | M1 dashboard displayed unnecessary Get Started button | Sprint 3 | Madhukiran | UI | Removed Get Started button and retained Run AI Analysis | 2026-09-20 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others